## 1. Effort
2500000
Effort By Module and Role
|  | Effort (MD) | [5 empty] | Cost (USD)
# | Module | Total (MD) | BE Coding (MD) | FE/Mobile Coding (MD) | Requirement Analysis (MD) | Testing (MD) | Project Management (MD) | Total (USD) | BE Coding (USD) | FE/Mobile Coding (USD) | Requirement Analysis (USD) | Testing (USD) | Project Management (USD)
I
I.A
I.B
II
II.A
II.B
II.C
II.D
II.E
III
III.A
III.B
TOTAL

## 2. WBS
|  | Project Code | AIFR
WBS OF AI FINANCIAL ANALYSIS, EVIDENCE & REFERENCE-CHECK PLATFORM
| # | Ref. Code | Features | Description | Total (MD) | BE Coding (MD) | FE/Mobile Coding (MD) | Requirement Analysis (MD) | Testing (MD) | Project Management (MD) | Remark | Optimistic (O) | Most-likely (M) | Pessimistic (P) | P50 (md) | P80 (md) | Definition of Done
I | I | SET UP & INSTALLATION
A | I.A | Requirement Gathering & BA
1 |  | Requirements
| 1 |  | AIFR scope, workflow and acceptance requirements | Confirm analyst workflow, input/output contract, review states, exception paths, and release acceptance criteria. |  |  |  | 6 |  |  | BA-only requirements work | 5 | 6 | 8 | 6.1667 | 6.5877 | Approved BRD/workflow map; Acceptance criteria mapped to WBS items
| 2 |  | Financial ratio, health rule and benchmark requirements | Elicit ratio formulas, deterministic rule precedence, health bands, benchmark comparison rules, and exception handling. |  |  |  | 4 |  |  | BA-only requirements work | 3 | 4 | 6 | 4.1667 | 4.5877 | Signed-off ratio/rule catalog; Benchmark governance decisions recorded
| 3 |  | Evidence, audit, security and explainability requirements | Define source hierarchy, citation/provenance fields, audit events, access controls, PII handling, and analyst note expectations. |  |  |  | 3 |  |  | BA-only requirements work | 2 | 3 | 5 | 3.1667 | 3.5877 | Evidence and audit schema requirements approved; Security and explanation acceptance criteria approved
B | I.B | AI Runtime Integration & Operational Readiness
1 |  | Runtime integration
| 4 |  | vLLM/SGLang model endpoint integration | Integrate the existing vLLM/SGLang endpoint, retries/timeouts, model selection, and health checks; excludes runtime installation/base setup. |  | 6 |  |  |  |  | Existing serving setup; endpoint integration only | 4 | 6 | 8 | 6 | 6.5613 | Endpoint health check passes; Timeout/retry behavior tested; No runtime installation work included
| 5 |  | Tool-calling contract tests and adapter harness | Implement JSON-schema tool-call contracts, mock tool adapters, invalid-call fixtures, and compatibility tests for the approved model endpoint. |  | 5 |  |  |  |  | Contract tests only; no frontend/mobile coding | 3 | 5 | 7 | 5 | 5.5613 | Valid and invalid tool-call fixtures pass; Schema-version compatibility test passes; Contract test report committed
| 6 |  | Model endpoint performance validation | Run representative prompt/tool-call load tests, measure latency/token throughput, and document concurrency limits and fallback thresholds. |  | 4 |  |  |  |  | Validation of existing runtime only | 3 | 4 | 6 | 4.1667 | 4.5877 | Latency and throughput baseline recorded; Performance limits and fallback thresholds approved
II | II | DEVELOPMENT
A | II.A | AI Models & Orchestration
1 |  | Agent implementations
| 7 |  | Main Agent / LangGraph-DeepAgent orchestration | Implement the typed state graph, task routing, checkpoint/resume, agent hand-offs, bounded retries, and terminal result assembly for the financial analysis workflow. |  | 6 |  |  |  |  | Concrete orchestration implementation | 4 | 6 | 8 | 6 | 6.5613 | Graph completes happy-path workflow; Checkpoint/resume preserves state; Retry limits and terminal errors are covered by tests
| 8 |  | Financial Ratio Agent | Implement the agent adapter that requests normalized financial inputs, invokes deterministic ratio tools, and returns ratio results with source-field references. |  | 6 |  |  |  |  | Agent-specific backend work | 4 | 6 | 8 | 6 | 6.5613 | Agent invokes only registered ratio tools; Outputs include ratio IDs and source references; Missing-input path is handled deterministically
| 9 |  | Health Evaluation Agent | Implement health-band evaluation agent that consumes computed ratios and rule outcomes, identifies drivers, and emits structured health findings. |  | 5 |  |  |  |  | Agent-specific backend work | 3 | 5 | 7 | 5 | 5.5613 | Health findings conform to schema; Each finding links to ratio/rule evidence; Threshold and exception cases are tested
| 10 |  | Reference-Check Agent | Implement dependency/reference lookup agent using evidence search and graph queries to compare declared relationships against retrieved records. |  | 5 |  |  |  |  | Agent-specific backend work | 3 | 5 | 7 | 5 | 5.5613 | Reference queries return ranked evidence; Neo4j relationship checks are represented in output; No-evidence result is explicit and non-hallucinatory
| 11 |  | Industry Benchmark Agent | Implement benchmark retrieval agent that selects governed peer sets, applies period/industry filters, and returns comparable metrics with coverage metadata. |  | 5 |  |  |  |  | Agent-specific backend work | 3 | 5 | 7 | 5 | 5.5613 | Peer selection uses approved governance rules; Benchmark outputs include period and coverage fields; Out-of-coverage behavior is tested
| 12 |  | Explanation & Note Agent | Implement evidence-grounded explanation and analyst-note generation with citations, confidence/limitations, and editable note sections. |  | 5 |  |  |  |  | Agent-specific backend work | 3 | 5 | 7 | 5 | 5.5613 | Every explanation claim has evidence references or limitation text; Note schema validates; Prompt-injection and unsupported-claim fixtures are rejected
| 13 |  | Recommendation Support Agent | Implement recommendation-support agent that turns validated findings into prioritized support points, assumptions, and analyst follow-up questions; it does not make autonomous credit decisions. |  | 4 |  |  |  |  | Decision support only; human analyst remains accountable | 3 | 4 | 6 | 4.1667 | 4.5877 | Recommendations link to validated findings; Assumptions and follow-up questions are explicit; Autonomous approval/decline output is impossible
| 14 |  | Tool Gateway and Output Validator | Implement authenticated tool registry, request/response envelopes, schema validation, provenance propagation, allowlists, and final output validation before analyst delivery. |  | 6 |  |  |  |  | Shared gateway and safety boundary | 4 | 6 | 8 | 6 | 6.5613 | Only allowlisted tools can be called; Malformed tool/result payloads are rejected; Validated output contains provenance and audit correlation ID
B | II.B | Deterministic Financial-Ratio & Rule Logic
1 |  | Deterministic logic
| 15 |  | Deterministic financial ratio calculation library | Implement versioned ratio formulas, input normalization, denominator/zero handling, rounding, and calculation trace records for the approved ratio catalog. |  | 6 |  |  |  |  | No LLM arithmetic; deterministic backend logic | 4 | 6 | 8 | 6 | 6.5613 | Golden test vectors pass; Formula version and inputs are recorded; Invalid/zero denominator behavior is deterministic
| 16 |  | Deterministic health bands and rule engine | Implement configurable threshold rules, precedence, severity mapping, exception rules, and rule-evaluation evidence for health classification. |  | 5 |  |  |  |  | Rules execute outside the model | 3 | 5 | 7 | 5 | 5.5613 | Threshold boundary tests pass; Rule version and precedence are traceable; Rule outcomes expose reasons and evidence
| 17 |  | Financial input normalization and validation | Implement typed ingestion of financial statement fields, unit/period normalization, required-field checks, and structured data-quality errors. |  | 4 |  |  |  |  | Backend-only deterministic validation | 3 | 4 | 6 | 4.1667 | 4.5877 | Units and periods normalize consistently; Required-field and quality errors are structured; Normalized fixtures feed ratio golden tests
C | II.C | Knowledge & Evidence
1 |  | Vector DB + Neo4j evidence
| 18 |  | Evidence document ingestion and chunk metadata | Implement MinIO document retrieval, parsing/chunking metadata, source identifiers, period/company tags, and ingestion status tracking. |  | 4 |  |  |  |  | Evidence backend only | 3 | 4 | 6 | 4.1667 | 4.5877 | Documents produce stable chunk/source IDs; Ingestion failures are retryable and observable; Metadata supports company and period filtering
| 19 |  | Vector DB retrieval and provenance service | Implement embedding-service/Qdrant indexing and similarity retrieval with filters, citation spans, source ranking, and provenance-preserving response objects. |  | 5 |  |  |  |  | Qdrant integration; no frontend/mobile coding | 3 | 5 | 7 | 5 | 5.5613 | Indexed fixtures are retrievable by semantic and metadata filters; Results include source spans and scores; Provenance survives tool gateway validation
| 20 |  | Neo4j evidence graph and relationship queries | Implement graph entities/relationships for companies, documents, references, and dependencies plus parameterized reference-check queries and graph backup metadata. |  | 4 |  |  |  |  | Neo4j evidence backend only | 3 | 4 | 6 | 4.1667 | 4.5877 | Graph constraints and seed fixtures load; Reference queries return explainable paths; Graph evidence IDs map to source records
D | II.D | Benchmark & Reference Check
1 |  | Benchmark governance
| 21 |  | Benchmark dataset governance and peer-set rules | Implement governed benchmark dataset versioning, peer inclusion/exclusion rules, metric definitions, period alignment, and approval metadata. |  | 4 |  |  |  |  | Governance and backend enforcement | 3 | 4 | 6 | 4.1667 | 4.5877 | Dataset versions and approvals are persisted; Peer-set rule tests pass; Metric definitions and periods are queryable
| 22 |  | Reference-check evidence comparison service | Implement comparison of declared references to retrieved graph/vector evidence, conflict flags, confidence fields, and analyst-review queue payloads. |  | 5 |  |  |  |  | Backend comparison service | 3 | 5 | 7 | 5 | 5.5613 | Match/mismatch/unknown states are distinct; Conflicts include supporting evidence IDs; Review payload is schema-valid
E | II.E | AI Audit, Security & Observability
1 |  | AI audit, security & observability
| 23 |  | AI audit trail and prompt/tool event capture | Implement immutable correlation-linked audit events for prompts, model responses, tool calls, rule versions, evidence IDs, and analyst overrides. |  | 3 |  |  |  |  | Audit backend | 2 | 3 | 5 | 3.1667 | 3.5877 | End-to-end correlation ID is queryable; Sensitive fields are redacted per policy; Audit events cover model, tool, rule, and override actions
| 24 |  | AI security controls and abuse defenses | Implement service authentication/authorization, secret lease usage, prompt-injection checks, PII redaction, tool allowlists, and rate/size limits. |  | 3 |  |  |  |  | Security controls only; infrastructure base exists | 2 | 3 | 5 | 3.1667 | 3.5877 | Unauthorized tool/service calls are denied; Prompt-injection and oversized payload tests pass; Secrets are not emitted in logs or outputs
| 25 |  | AI observability, traces and quality signals | Implement OpenTelemetry traces, model/tool latency metrics, failure counters, evidence coverage signals, and dashboards/alerts for operational review. |  | 4 |  |  |  |  | Observability integration, not platform installation | 3 | 4 | 6 | 4.1667 | 4.5877 | Trace spans cover orchestration and tool calls; Latency/error/evidence-coverage metrics are emitted; Alert thresholds are documented and tested
III | III | TESTING & DEPLOYMENT SUPPORT
A | III.A | Solution Qualification
1 |  | Qualification testing
| 26 |  | Solution qualification: integration, evidence and safety test pack | Execute qualification against representative financial cases: end-to-end agent graph, deterministic ratio/rule golden vectors, Qdrant/Neo4j evidence, schema validation, security abuse cases, and model endpoint performance thresholds. |  | 6 |  |  |  |  | Backend/QC qualification support; no frontend/mobile coding | 4 | 6 | 8 | 6 | 6.5613 | SIT/UAT test report completed; Critical defects fixed or accepted; Evidence coverage and safety gates pass; Release recommendation signed off
B | III.B | Minimal Deployment & Maintenance Support
1 |  | Minimal deployment & maintenance
| 27 |  | Production deployment and rollback runbook | Apply the existing runtime deployment path, configure service endpoint references/secrets, execute smoke checks, and document rollback; excludes infrastructure/base serving installation. |  | 1 |  |  |  |  | Minimal deployment only; PM=0 | 1 | 1 | 2 | 1.1667 | 1.307 | Production smoke test passes; Rollback steps are verified; No vLLM/SGLang installation is estimated
| 28 |  | Minimal post-go-live defect support | Provide a short stabilization window for backend defects, configuration corrections, and audit/observability tuning; no feature expansion. |  | 2 |  |  |  |  | Minimal maintenance support only | 1 | 2 | 3 | 2 | 2.2807 | Accepted production defects triaged and resolved; Operational handover notes completed; Support window closed with open-items log

## 3. Delivery Plan
Master Plan
|  |  |  | 1st Month |  |  |  | 2nd Month |  |  |  | 3rd Month
|  |  |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6
# | Module | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
I.A |  | W1 | W1
I.B |  | W2 | W2
II.A |  | W3 | W7
II.B |  | W8 | W8
II.C |  | W9 | W9
II.D |  | W10 | W10
II.E |  | W11 | W11
III.A |  | W12 | W12
III.B |  | W12 | W12
Resource Planning
1 | Project Manager | TBD | TBD
2 | Technical Lead | TBD | TBD
3 | Developer | TBD | TBD
4 | Business Analyst | TBD | TBD
5 | Quality Controller | TBD | TBD
6 | Designer | TBD | TBD
7 | Devops | TBD | TBD
# | Deliverables Milestone | Start | End | Deliverables
1 | Contract Signoff | TBD | TBD | Signed contract
2 | Requirement Confirmation/Signoff | TBD | TBD | BRD
3 | Development Completion and UAT Initiation | TBD | TBD | System ready in UAT, Test Cases, Test Report
4 | Completion of UAT | TBD | TBD | Source Code, User Guide, Technical Specification
5 | Completion of Post-Launch Support | TBD | TBD | Maintenance log

## 4. Master Data
BU
Role | Percent on Dev | Remark
PM | 0.1 | in total (dev + ba + qc)
BA | 0.1
Developer
QC | 0.3
OB
Role | Rate
PM | 200
BA | 130
Developer | 150
QC | 110