## 0. How to use
File Structure
Sheet | Description
1. Effort | The sheet provides the overall effort to develop a end-to-end solution (based on the client need)
2. WBS | The sheet provides the work break down structure with the whole effort to complete the project.
2. Delivery Plan | The sheet provide the delivery plan, the resource allocation, the milestone
4. Master Data | The sheet provide the configuration to adjust the effort rate
Highlight | Remark
1 | Based on the client expectation & deliverables, BU can update the Module accordingly. Eg. If the client requests UI/UX design, please update the effort. Or, remove that row.
2 | in the "Fix SIT/UAT Issues" item, please provide your expected room for our client to handle the enhancement & the Change Request WITHOUT CHARGED.
3

## 1. Effort
2500000
Effort By Module and Role
|  | Effort (MD) | [5 empty] | Cost (USD)
# | Module | Total (MD) | BE Coding (MD) | FE/Mobile Coding (MD) | Requirement Analysis (MD) | Testing (MD) | Project Management (MD) | Total (USD) | BE Coding (USD) | FE/Mobile Coding (USD) | Requirement Analysis (USD) | Testing (USD) | Project Management (USD)
I | SET UP & INSTALLATION | 31.5 | 30 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
I.A | Solution Design | 19.95 | 19 | 0 | 0 | 0 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0
I.B | System Operation | 11.55 | 11 | 0 | 0 | 0 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0
II | DEVELOPMENT | 51.45 | 18.25 | 16.75 | 3.5 | 10.5 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0
II.A | Web Portal | 11.76 | 3.25 | 4.75 | 0.8 | 2.4 | 0.56 | 0 | 0 | 0 | 0 | 0 | 0
II.B | Mobile Application | 17.64 | 3 | 9 | 1.2 | 3.6 | 0.84 | 0 | 0 | 0 | 0 | 0 | 0
II.C | Core Service | 22.05 | 12 | 3 | 1.5 | 4.5 | 1.05 | 0 | 0 | 0 | 0 | 0 | 0
III | TESTING & DEPLOYMENT SUPPORT | 49.57 | 17 | 18 | 3.1 | 9.3 | 2.17 | 0 | 0 | 0 | 0 | 0 | 0
III.A | Solution Qualification | 8.82 | 3 | 3 | 0.6 | 1.8 | 0.42 | 0 | 0 | 0 | 0 | 0 | 0
III.B | Deployment & Maintenance | 40.75 | 14 | 15 | 2.5 | 7.5 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 132.52 | 65.25 | 34.75 | 6.6 | 19.8 | 6.12 | 0 | 0 | 0 | 0 | 0 | 0

## 2. WBS
|  | Project Code | BNK
WBS OF OUR_SOLUTION_NAME
| # | Ref. Code | Features | Description | Total (MD) | BE Coding (MD) | FE/Mobile Coding (MD) | Requirement Analysis (MD) | Testing (MD) | Project Management (MD) | Remark
[5 empty] | 132.52 | 65.25 | 34.75 | 6.6 | 19.8 | 6.12
| I | SET UP & INSTALLATION |  |  | 31.5 | 30 | 0 | 0 | 0 | 1.5 |  | Depend on the client expectation to tailor the WBS
A | I.A | Solution Design |  |  | 19.95 | 19 | 0 | 0 | 0 | 0.95
| 1 | BNK-1 | Database Design | + Design Database Schema + Set up DB Cluster | 1.05 | 1 | - |  |  | 0.05 |  | Just by case
| 2 | BNK-2 | System Design | + High-Level Architecture Design + Network Architecture + Component Design + High Availability and Redundancy | 5.25 | 5 | - |  |  | 0.25 |  | Just by case
| 3 | BNK-3 | Data Security | + Set up the data encryption + Set up the encrypt traffic | 1.05 | 1 | - |  |  | 0.05 |  | Just by case
| 4 | BNK-4 | UI/UX Design |  | 10.5 | 10 | - |  |  | 0.5 |  | Just by case
| 5 | BNK-5 | Code Base Setup | + Set up the microservice & network | 2.1 | 2 | - |  |  | 0.1 |  | Just by case
B | I.B | System Operation |  |  | 11.55 | 11 | 0 | 0 | 0 | 0.55
| 6 | BNK-6 | Deployment Setup | + Setup the infrastructure + Setup deployment CI/CD pipeline + Set up the Code Quality Pipeline (SonarQube) + Deploy to DEV/UAT/PROD | 5.25 | 5 | - |  |  | 0.25 |  | Just by case
| 7 | BNK-7 | Infrastructure Monitoring | + Set up the Logger System (Prometheus) + Set up the Monitoring System (Grafana) + Set up the alert threadhold to Admin | 2.1 | 2 | - |  |  | 0.1 |  | Just by case
| 8 | BNK-8 | Front-end & Mobile Error Monitoring | + Set up the Error Monitoring (Sentry) | 2.1 | 2 | - |  |  | 0.1 |  | Just by case
| 9 | BNK-9 | Application Performance Monitoring | + Set up the Application Performance Monitoring solution (Elastic APM) | 2.1 | 2 | - |  |  | 0.1 |  | Just by case
II | II | DEVELOPMENT |  |  | 51.45 | 18.25 | 16.75 | 3.5 | 10.5 | 2.45
A | II.A | Web Portal |  |  | 11.76 | 3.25 | 4.75 | 0.8 | 2.4 | 0.56
1 | II.A.1 | Common Module
| 10 | BNK-10 | Common Frame |  | 2.205 |  | 1.5 | 0.15 | 0.45 | 0.105
| 11 | BNK-11 | Authentication & Authorization | + Login/logout + Forgot Password | 1.47 | 0.5 | 0.5 | 0.1 | 0.3 | 0.07
2 | II.A.2 | Your Module | [9 empty] | sample
| 12 | BNK-12 | Entity Management | + List, soft, filter, export to Excel | 2.205 | 0.75 | 0.75 | 0.15 | 0.45 | 0.105
| 13 | BNK-13 | Entity Management - Detail |  | 5.88 | 2 | 2 | 0.4 | 1.2 | 0.28
B | II.B | Mobile Application |  |  | 17.64 | 3 | 9 | 1.2 | 3.6 | 0.84
1 | II.B.1 | Common Module | [9 empty] | sample
| 14 | BNK-14 | Common Frame |  | 2.94 | 0 | 2 | 0.2 | 0.6 | 0.14
| 15 | BNK-15 | Authentication & Authorization |  | 1.47 |  | 1 | 0.1 | 0.3 | 0.07
2 | II.B.2 | Your Module | [9 empty] | sample
| 16 | BNK-16 | Entity Management | + List, soft, filter, export to Excel | 6.615 | 1.5 | 3 | 0.45 | 1.35 | 0.315
| 17 | BNK-17 | Entity Management - Detail |  | 6.615 | 1.5 | 3 | 0.45 | 1.35 | 0.315
C | II.C | Core Service |  |  | 22.05 | 12 | 3 | 1.5 | 4.5 | 1.05
1 | II.C.1 | Notification | [9 empty] | sample
| 18 | BNK-18 | Notification Adapter | Implement the notification adapter to handle various notification types | 2.94 | 2 |  | 0.2 | 0.6 | 0.14
| 19 | BNK-19 | Email Notification | Implement the email notification (Request, Response, Error Handling) | 1.47 | 1 |  | 0.1 | 0.3 | 0.07
| 20 | BNK-20 | SMS Notification | Implement the App-to-Person notification (Request, Response, Error Handling) | 1.47 | 1 |  | 0.1 | 0.3 | 0.07
| 21 | BNK-21 | In-App Notification | Implement the App-to-App notification (Request, Response, Error Handling) | 1.47 | 1 |  | 0.1 | 0.3 | 0.07
| 22 | BNK-22 | Whatapps Integration |  | 1.47 | 1 |  | 0.1 | 0.3 | 0.07
2 | II.C.2 | 3rd-party Integration | [9 empty] | sample
| 23 | BNK-23 | Real-time chat engine |  | 5.88 | 1 | 3 | 0.4 | 1.2 | 0.28
| 24 | BNK-24 | Public API | Expose the OpenAPI for 3rd party | 1.47 | 1 |  | 0.1 | 0.3 | 0.07
| 25 | BNK-25 | SSO Integration | Integrate with the client SSO | 1.47 | 1 |  | 0.1 | 0.3 | 0.07
| 26 | BNK-26 | Payment Gateway | Integrate with the payment gateway | 1.47 | 1 |  | 0.1 | 0.3 | 0.07
3 | II.C.3 | AI | [9 empty] | sample
| 27 | BNK-27 | IDP Customization |  | 0 |  |  | 0 | 0 | 0
| 28 | BNK-28 | IDP Integration |  | 2.94 | 2 |  | 0.2 | 0.6 | 0.14
| III | TESTING & DEPLOYMENT SUPPORT |  |  | 49.57 | 17 | 18 | 3.1 | 9.3 | 2.17
A | III.A | Solution Qualification |  |  | 8.82 | 3 | 3 | 0.6 | 1.8 | 0.42
1 | III.A.1 | Testing & Quality Assurance
| 29 | BNK-29 | Fix Load Test Report | Fix the load test issue to meet the client standard | 2.94 | 1 | 1 | 0.2 | 0.6 | 0.14 |  | Just by case
| 30 | BNK-30 | Fix Security Test Report | Fix the security test issue to meet the client standard | 2.94 | 1 | 1 | 0.2 | 0.6 | 0.14 |  | Just by case
| 31 | BNK-31 | Fix SIT/UAT Issues | Support user to test, handle the enhancement to meet the needs within x month. => CR Effort (non-charged): xxx MDs | 2.94 | 1 | 1 | 0.2 | 0.6 | 0.14
B | III.B | Deployment & Maintenance |  |  | 40.75 | 14 | 15 | 2.5 | 7.5 | 1.75
1 | III.B.1 | Deployment & Launch
| 32 | BNK-32 | Production Deployment | Deploy web, mobile, and API components to production | 1 | 1 | [5 empty] | Just by case
| 33 | BNK-33 | App Store Submission (for Mobile) | Submit mobile applications to the iOS App Store and Google Play Store | 1 | 1 | [5 empty] | Just by case
| 34 | BNK-34 | Data Migration |  | 1 | 1 | [5 empty] | Just by case
2 | III.B.2 | Maintenance & Transition
| 35 | BNK-35 | Post Golive Support | Support use to fix PROD defect in x month | 36.75 | 10 | 15 | 2.5 | 7.5 | 1.75
| 36 | BNK-36 | Project Transition | Prepare & transfer the document to transfer (BRD, Tech Spec, User Guide, Deployment Guide) | 1 | 1 | [5 empty] | Just by case

## 3. Delivery Plan (By Month)
Master Plan
| Master Planning |  |  | 1st Month |  | 2nd Month |  | 3rd Month |  | 4th Month |  | 5th Month |  | 6th Month |  | 7th Month |  | 8th Month |  | 9th Month
# | Module | Start | End | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18
| REQUIREMENT GATHERING | TBD | TBD
I | SET UP & INSTALLATION | TBD | TBD
I.A | Solution Design | TBD | TBD
I.B | System Operation | TBD | TBD
II | DEVELOPMENT | TBD | TBD
II.A | Web Portal | TBD | TBD
II.B | Mobile Application | TBD | TBD
II.C | Core Service | TBD | TBD
III | TESTING & DEPLOYMENT SUPPORT | TBD | TBD
III.A | Solution Qualification | TBD | TBD | [12 empty] | UAT
III.B | Deployment & Maintenance | TBD | TBD | [14 empty] | Nursing
# | Resource Planning | Start | End | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18
1 | Project Manager | TBD | TBD | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2
2 | Technical Lead |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | Developer |  |  |  | 2 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 1 | 1 | 1 | 1
4 | Business Analyst | TBD | TBD | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 | Quality Controller | TBD | TBD |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Designer | TBD | TBD |  | 1 | 1
7 | Devops | TBD | TBD |  | 1 | [10 empty] | 0.2 |  | 0.2 |  |  |  | 682
| TOTAL |  |  | 1.8 | 7.3 | 6.3 | 6.3 | 7.3 | 7.3 | 7.3 | 7.3 | 7.3 | 7.3 | 7.3 | 7.3 | 3.5 | 3.3 | 1.4 | 1.2 | 1.2 | 1.2 | 919
# | Deliverables Milestone | Start | End | Deliverables
1 | Contract signoff | TBD | TBD | Contract Signoff
2 | Requirement Confirmation/Signoff | TBD | TBD | BRD
3 | Development Completion and UAT Initiation | TBD | TBD | System is ready in UAT + Test cases / Test Report
4 | Completion of UAT | TBD | TBD | Soure code + User Guide + Tech Specification
5 | Completion of Post-Launch Support | TBD | TBD
2
1
3
4
5

## 3. Delivery Plan
Master Plan
|  |  |  | 1st Month |  |  |  | 2nd Month |  |  |  | 3rd Month |  |  |  | 4th Month |  |  |  | 5th Month
| Master Planning |  |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9 |  | Sprint 10
# | Module | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
| REQUIREMENT GATHERING | TBD | TBD
I | SET UP & INSTALLATION | TBD | TBD
I.A | Solution Design | TBD | TBD
I.B | System Operation | TBD | TBD
II | DEVELOPMENT | TBD | TBD
II.A | Web Portal | TBD | TBD
II.B | Mobile Application | TBD | TBD
II.C | Core Service | TBD | TBD
III | TESTING & DEPLOYMENT SUPPORT | TBD | TBD
III.A | Solution Qualification | TBD | TBD | [12 empty] | UAT
III.B | Deployment & Maintenance | TBD | TBD | [16 empty] | Nursing
# | Resource Planning | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W17 | W18
1 | Project Manager | TBD | TBD | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | Technical Lead
3 | Developer
4 | Business Analyst | TBD | TBD | 1 | 0.5
5 | Quality Controller | TBD | TBD |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Designer | TBD | TBD |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Devops | TBD | TBD |  | 0.2 | [8 empty] | 0.2 |  | 0.2
| TOTAL |  |  | 2 | 2.2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3.2 | 3 | 3.2
# | Deliverables Milestone | Start | End | Deliverables | [16 empty] | OB works with client to finalize this milestone
1 | Contract signoff | TBD | TBD | Contract Signoff
2 | Requirement Confirmation/Signoff | TBD | TBD | BRD
3 | Development Completion and UAT Initiation | TBD | TBD | System is ready in UAT + Test cases / Test Report
4 | Completion of UAT | TBD | TBD | Soure code + User Guide + Tech Specification
5 | Completion of Post-Launch Support | TBD | TBD
2
1
3
4
5

## 4. Master Data
BU
Role | Percent on Dev | Remark
PM | 0.05 | in total (dev + ba + qc)
BA | 0.1
Developer
QC | 0.3
OB
Role | Rate
PM
BA
Developer
QC

## 1. Effort Summary_By PP_BK (hidden)
2500000
Effort By Module and Role
# | Module |  | Total (MD) | BE (MD) | FE (MD) | BA (MD) | QC (MD) | PM (MD)
Client Portal
1 | Registration |  | 12.495 | 3.5 | 5 | 0.85 | 2.55 | 0.595
2 | Login |  | 4.41 | 1 | 2 | 0.3 | 0.9 | 0.21
3 | Dashboard |  | 4.62 | 1.5 | 1.5 | 0.3 | 0.9 | 0.42
4 | Funder |  | 40.04 | 12.5 | 13.5 | 2.6 | 7.8 | 3.64
5 | Account |  | 9.24 | 3.5 | 2.5 | 0.6 | 1.8 | 0.84
Admin Portal
1 | Login |  | 5.39 | 1.5 | 2 | 0.35 | 1.05 | 0.49
2 | Member |  | 113.19 | 35.5 | 38 | 7.35 | 22.05 | 10.29
3 | KYC |  | 12.32 | 3 | 5 | 0.8 | 2.4 | 1.12
4 | Admin |  | 8.47 | 2.5 | 3 | 0.55 | 1.65 | 0.77
Other
1 | - Multi Language - Integrate - Access Control - Integration with 3rd parties (KYC, Twilio) |  | 33.88 | 4 | 18 | 2.2 | 6.6 | 3.08
Deployment
1 | Deployment + Solution Architecture (database design, setup source code BE/FE) | Setup pipeline, CICD, deploy to DEV/UAT/PROD environment | 10
| TOTAL |  | 254.055 | 68.5 | 90.5 | 15.9 | 47.7 | 21.455
12.7027
Rate Card
# | Function | Daily Rate (€)
1 | S-PM
2 | S-BA
3 | M-DEV
4 | M-QA
5 | S-Devops
TOTAL
Costing
# | Module |  | Total (€) | BE (€) | FE (€) | BA (€) | QC (€) | PM (€) | Devops (€)
Client Portal
1 | Registration |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Login |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Dashboard |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Funder |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Account |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Admin Portal
1 | Login |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Member |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | KYC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Admin |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other
1 | - Multi Language - Integrate - Access Control |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deployment
1 | Setup pipeline, CICD, deploy to DEV/UAT/PROD environment | Setup pipeline, CICD, deploy to DEV/UAT/PROD environment | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assuming the team will have 1 Technical Leader, 1 middle QC, 3 middle Dev, 1 Devops

## 3. WBS_General_BK (hidden)
WBS OF LENDING SYSTEM FOR PROPCAP
# | Ref. Code | Screen Name | Features | Total (MD) | BE | FE | BA | QC | PM (coordinate only) | Remark
|  |  |  | 244.86 | 68.5 | 90.5 | 15.9 | 47.7 | 22.26
Client Portal |  |  |  | 71.61 | 22 | 24.5 | 4.65 | 13.95 | 6.51
Registration |  |  |  | 13.09 | 3.5 | 5 | 0.85 | 2.55 | 1.19
1 | LS.CP-1 | Frontend-Registration | 1. Select Button 2. Corporate/Individual 3. Popup Warning (Popup-warning-cor) | 0.5 | 0.5 | 0 | 0.05 | 0.15 | 0.07
2 | LS.CP-2 | Frontend-Registration-form-cor | For Corporation 1. Validation handle 2. Create My Account/Receive direct marketing Check box 3. Platform Usage Disclaimer (Popup - Platform Usage Disclaimer – cor) 4. Term and Conditional (Popup - Terms and Conditions – cor) 5. Personal Data Privacy Policy (Popup - Personal Data Privacy Policy – cor) | 3 | 1 | 2 | 0.3 | 0.9 | 0.42
3 | LS.CP-3 | Frontend - ActiveAC – cor | For Corporation 1. Authentication 2. Resend/Submit | 1 | 0.5 | 0.5 | 0.1 | 0.3 | 0.14
4 | LS.CP-4 | Frontend - Registration – form | For Individual 1. Validation handle 2. Create My Account/Receive direct marketing Check box 3. Platform Usage Disclaimer (Popup - Platform Usage Disclaimer) 4. Term and Conditional (Popup - Terms and Conditions) 5. Personal Data Privacy Policy (Popup - Personal Data Privacy Policy) | 3 | 1 | 2 | 0.3 | 0.9 | 0.42
5 | LS.CP-5 | Frontend - ActiveAC | For Individual 1. Authentication 2. Resend/Submit | 1 | 0.5 | 0.5 | 0.1 | 0.3 | 0.14
Login |  |  |  | 4.62 | 1 | 2 | 0.3 | 0.9 | 0.42
6 | LS.CP-4 | Frontend-Login | 1. Authentication 2. Forgot Password/Login Button | 1.5 | 0.5 | 1 | 0.15 | 0.45 | 0.21
7 | LS.CP-5 | Frontend-Login-OTP | 1. Auto send email OTP 2. Authentication OTP 3. Submit/Resend OTP | 0.5 | 0 | 0.5 | 0.05 | 0.15 | 0.07
8 | LS.CP-6 | Frontend - Forget Password | 1. Authentication 2. Request password reset/Back to Login 3. Send auto email | 1 | 0.5 | 0.5 | 0.1 | 0.3 | 0.14
Dashboard |  |  |  | 4.62 | 1.5 | 1.5 | 0.3 | 0.9 | 0.42
9 | LS.CP-7 | Frontend - Dashboard - individual | 1. Navigation Menu 2. Become a Funder 3. Become a Borrower/Guarantor 4. Logout | 1 | 0.5 | 0.5 | 0.1 | 0.3 | 0.14
10 | LS.CP-8 | Frontend - Dashboard – DocsSubmitted | 1. Navigation Menu 2. Become a Funder/Become a Borrower 3. Status Management 4. Invest a deal/Submit a mortgage deal 5. Logout | 1 | 0.5 | 0.5 | 0.1 | 0.3 | 0.14
11 | LS.CP-9 | Frontend - FunderBorrower_Dashboard | 1. Navigation Menu 2. Invest a deal/Submit a mortgage deal 3. Logout | 1 | 0.5 | 0.5 | 0.1 | 0.3 | 0.14 | BnK Q&A (No.1) Maybe Design was wrong, this screen show when click proffile account
Funder |  |  |  | 40.04 | 12.5 | 13.5 | 2.6 | 7.8 | 3.64
12 | LS.CP-10 | Frontend - Funder - Individual - Borrowers and Guarantors | Account Details 1. Process 5 Step 2. Select Currency/Personal Detail/Contact Detail 3. Save and Next/Cancel/Submit | 10 | 5 | 5 | 1 | 3 | 1.4
11 | LS.CP-11 | Frontend - Funder - Individual - Employment Details | Employment Details 1. Process 5 Step 2. Employment Details 3. Save and Next/Cancel/Submit/Back 4. Change status Previous Step and hint this step | 2 | 1 | 1 | 0.2 | 0.6 | 0.28
12 | LS.CP-12 | Frontend - Funder - Individual - Loan Lending Criteria | Loan Lending Criteria 1. Process 5 Step 2. Loan Lending Criteria 3. Save and Next/Cancel/Submit 4. Change status Previous Step and hint this step | 4 | 2 | 2 | 0.4 | 1.2 | 0.56
13 | LS.CP-13 | Frontend - Funder - Individual - Bank Ac | Bank Account Information 1. Process 5 Step 2. Bank Account Information 3. Save and Next/Cancel/Submit 4. Change status Previous Step and hint this step | 2 | 1 | 1 | 0.2 | 0.6 | 0.28
14 | LS.CP-14 | Frontend - Funder - Individual - SupportingDoc | Supporting Document 1. Process 5 Step 2. Personal Level 3. Save as Draft/Cancel/Submit/Dowload file/Delete File/ Upload file 4. Change status Previous Step and hint this step | 5 | 2 | 3 | 0.5 | 1.5 | 0.7
15 | LS.CP-15 | Frontend - Popup - Declaration Form | 1. Validation handle 2. Agree Button | 1 | 0.5 | 0.5 | 0.1 | 0.3 | 0.14
16 | LS.CP-16 | Frontend - Popup - Personal Information Collection Statement | 1. Validation handle 2. Agree Button | 1 | 0.5 | 0.5 | 0.1 | 0.3 | 0.14
17 | LS.CP-17 | Popup - PI - Funder - individual | 1. Validation handle 2. Agree Button | 1 | 0.5 | 0.5 | 0.1 | 0.3 | 0.14
Account |  |  |  | 9.24 | 3.5 | 2.5 | 0.6 | 1.8 | 0.84
18 | LS.CP-18 | Frontend - Borrower_Account | Account Information Tab 1. Account Information/ Personal Details/Contact Detail/Notication/Change Password | 5 | 3 | 2 | 0.5 | 1.5 | 0.7
19 | LS.CP-19 | Frontend - Borrower_Account – Document List | Document List Tab 1. Borrower Request (Dowload file) 2. Funder Request | 1 | 0.5 | 0.5 | 0.1 | 0.3 | 0.14
Admin Portal |  |  |  | 139.37 | 42.5 | 48 | 9.05 | 27.15 | 12.67
Login |  |  |  | 5.39 | 1.5 | 2 | 0.35 | 1.05 | 0.49
20 | LS.AP-1 | Backend - Login | 1. Authentication 2. Forgot Password/Login Button | 2 | 1 | 1 | 0.2 | 0.6 | 0.28
21 | LS.AP-2 | Backend - forget password | 1. Authentication 2. Request password reset/Back to Login 3. Send auto email | 1.5 | 0.5 | 1 | 0.15 | 0.45 | 0.21
Member |  |  |  | 113.19 | 35.5 | 38 | 7.35 | 22.05 | 10.29
22 | LS.AP-3 | Backend - Members - List of user | 1. Listing/Search/Sort/View/Reset/Paging/Add user/Dowload | 6 | 3 | 3 | 0.6 | 1.8 | 0.84
23 | LS.AP-4 | Backend - Members - Add User | 1. Auto-generate Password/Cancel/Submit | 2 | 1 | 1 | 0.2 | 0.6 | 0.28
24 | LS.AP-5 | Backend - Members - User detail - Basic Info. | Basic Information Tab 1. Edit/change status | 2 | 1 | 1 | 0.2 | 0.6 | 0.28
25 | LS.AP-6 | Backend - Members - User detail - Change Request | Change Request Tab 1. Listing/Sort/Add Change Request/Dowload/Save/Cancel/Delete 2. Status Management | 11 | 5 | 6 | 1.1 | 3.3 | 1.54
26 | LS.AP-7 | Backend - Members - User detail – Request of Funder -Individual | Funder Request Tab 1. Edit/Approve/Reject/KYC 2. Supporting Document Uploaded (List/Upload/Dowload/Delete) | 10 | 5 | 5 | 1 | 3 | 1.4
27 | LS.AP-8 | Backend - Members - User detail – Request of Borrower -Individual | Borrower/Guarantor Request Tab 1. Edit/Approve/Reject/KYC 2. Supporting Document Uploaded (List/Upload/Dowload/Delete) 3. Company KYC | 10 | 5 | 5 | 1 | 3 | 1.4
28 | LS.AP-9 | Backend - Members - User detail - Funder KYC_individual | Funder KYC Tab 1. Navigation mini (status management) 2. Edit/RunAML Screening Now/KYC Report/ Accept/Deny/Dowload/Go to Search/Full Detail/Add Comment 3. AML Checking 4. KYC Audit Trail (Paging) | 10 | 5 | 5 | 1 | 3 | 1.4
29 | LS.AP-10 | Backend - Members - User detail - Borrower KYC_corparate | Borrower/Guarantor KYC Tab 1. Navigation mini (status management) 2. Edit/RunAML Screening Now/KYC Report/ Accept/Deny/Dowload/Go to Search 3. Additional KYC Step (Add New Step/upload/Delete/Edit) 3. AML Checking 4. KYC Audit Trail (Paging) 5. Nova Credit (Generate Nova Credit Report) | 10 | 5 | 5 | 1 | 3 | 1.4
30 | LS.AP-11 | Backend - Members - User detail - Activity Log | Activity Log Tab 1. Listing/Sort/Dowload/Paging 2. Get all data activity | 1.5 | 0.5 | 1 | 0.15 | 0.45 | 0.21
31 | LS.AP-12 | Backend - Members - List of Request | 1. Listing/Sort/Search/Reset/Dowload/Paging 2. Status Management | 2.5 | 1 | 1.5 | 0.25 | 0.75 | 0.35
32 | LS.AP-13 | Backend - Members - List of Change Request | 1. Listing/Sort/Search/Reset/Dowload/Paging 2. Status Management | 2.5 | 1 | 1.5 | 0.25 | 0.75 | 0.35
33 | LS.AP-14 | Backend - Members - Add Change Request | 1. Search 2. Search Result (Backend - Members - Add Change Request – 1) | 6 | 3 | 3 | 0.6 | 1.8 | 0.84
KYC |  |  |  | 12.32 | 3 | 5 | 0.8 | 2.4 | 1.12
33 | LS.AP-14 | Backend - KYC - List of kyc | 1. Listing/Sort/Search/Reset/Dowload/Paging 2. Status Management | 2.5 | 1 | 1.5 | 0.25 | 0.75 | 0.35
34 | LS.AP-15 | Backend - KYC - Alert List | 1. Listing/Sort/Search/Reset/Dowload/Paging 2. Status Management 3. Alert | 3 | 1 | 2 | 0.3 | 0.9 | 0.42
35 | LS.AP-16 | Backend - KYC - Repositry | 1. Listing/Sort/Search/Reset/Dowload/Paging 2. Status Management | 2.5 | 1 | 1.5 | 0.25 | 0.75 | 0.35
Admin |  |  |  | 8.47 | 2.5 | 3 | 0.55 | 1.65 | 0.77
36 | LS.AP-17 | Backend - Admin - Audit Log List | 1. Listing/Sort/Search/Reset/Dowload/Paging 2. Get all data audit log | 1.5 | 0.5 | 1 | 0.15 | 0.45 | 0.21
37 | LS.AP-18 | Backend - Admin - Holiday Table | 1. Listing/Sort/Search/Import/Export 2. Validate upload data | 2 | 1 | 1 | 0.2 | 0.6 | 0.28
38 | LS.AP-19 | Backend - Admin - Currency Exchange | 1. Listing/Sort/Import/Export 2. Validate upload data | 2 | 1 | 1 | 0.2 | 0.6 | 0.28
Other |  |  |  | 33.88 | 4 | 18 | 2.2 | 6.6 | 3.08
39 | LS.AP-20 | Multi Language | 1. Change Language (English , Traditional Chinese and Simplified Chinese) | 2 | 2 | 0 | 0.2 | 0.6 | 0.28
40 | LS.AP-21 | Integrate | Twilio (OTP): call API for generating OTP + verify OTP | 5 | 0 | 5 | 0.5 | 1.5 | 0.7 | Spent time for research
41 | LS.AP-22 |  | Email: sending email + content for each use case | 5 | 0 | 5 | 0.5 | 1.5 | 0.7 | Spent time for research
42 | LS.AP-23 |  | Integrate with 3rd party API for KYC | 5 | 0 | 5 | 0.5 | 1.5 | 0.7 | Spent time for research
43 | LS.AP-24 | Access Control | For both Client Site and Admin Site (Only Screen + Key button (Accept/Deny)) 1. Client Site (Borrower/Funder/Nomineee) 2. Admin Site (Operation Team - General User/Operation Team - Operation Head (Approver)/IT Administrator (Super User) | 5 | 2 | 3 | 0.5 | 1.5 | 0.7

## 1. Effort Summary_General (hidden)
2500000
TGP for TG SPROUT
# | Task | Estimate (MD) | Unit Price | TOTAL | REMARK
1 | UIUX Design | 0 | 0 | 0 | user customer design
2 | Collect Requirement + Wrire SRS | #REF! | 0 | #REF! | 1. Collect + clarify + wireframe for new changes 2 Making documents : SRS, user guide 3. BA effort to follow up with developers to transfer requirements and validate output within the project timeline
3 | Solution + Coding | #REF! | 0 | #REF! | Do technical solution and coding to implement features/fix bugs
4 | Test plan/test cases + execute test | #REF! | 0 | #REF! | Output: test cases + execute test. QC tasks (cycle for each sprint): 1. Study requirements from BA/PM/Customers 2. Create test cases, making Testcase documents 3. Execute test 4. Log bugs + followup with dev to re-test + report to PM for testing progress/outstanding issues. 5. Regresstion test all feature before handover to UAT + before releasing to PROD.
5 | Setup + Deploy DEV/UAT + writing guideline | 8 | 0 | 0 | Do below tasks for each environment (DEV/UAT). If customer need us help to deploy on PROD, we can help also. 1. Create deployment pipeline in gitlab: build job + deploy job for each Microservice. (< 10 Microservice) 2. Verify to make sure these MS can call togethers. 3. Show logs for each MS. (It's for developers to troubelshoot when having issues in these invironments)
6 | Support users during UAT | 30 | 0 | 0 | UAT within 3 weeks. 1 dev and 1 BA/QC will support to test/fix bugs within this period
7 | Project Management and Teamwork | #REF! | 0 | #REF! | PM Effort (planning, executing, monitoring & controlling, directing, closing) + All team member effort for communication/grooming/planning/demo/retrospective to ensure for progress and quality
| TOTAL | #REF! |  | #REF!
#REF!
Post Golive support
# | Task | Support Duration (month) | Delivery Service (VND) | TOTAL (VND) | REMARK
1 | Support 3 months. | 3 | #REF! | #REF! | 1% total delivery service for each month
#REF!
TOTAL
| #REF! | (VND)
| #REF! | (USD)